## Slide 1: Using Large Language Models to Convert Documents to Knowledge Graphs to Check for Completeness and Consistency
Michael Wacey

## Slide 2: Praxis Health Check May 9, 2025
 | Research | Paper | Project
Overall Progress | ON TRACK Almost complete. I will just need to update it as I complete the paper. | ON TRACK Writing is going well, and I can keep on track. | ON TRACK Most of what I set out to do is done. I need to integrate some Hyperparameters for testing.
Issues Encountered | Newer topics are not widespread in peer reviewed journals. When a paper is published, I have switched to the peer reviewed version as a source. | Learning Overleaf and the template. Integration between RefWorks and Overleaf. | Nothing I have done so far makes nice charts and graphs. Orange may help with this.
Percent Complete | 90% | 30% | 70%
Anticipated Roadblocks | I will continue to have issues with arXiv sources. | Making the agreed scope of my paper clear and acceptable. | Showing that my approach is better. It is clearly better than a manual process but that is not numerical.