## Sheet1
Section | Name | Required Minimum | Required Maximum | From Page | To Page | Pages | Remaining | Under / Over | To Do
1 | Introduction | 5 | 7 | 1 | 7 | 7 | 0 | 0 | X | Write all content with placeholders
2 | Literature Review | 20 | 30 | 8 | 31 | 24 | 0 | 0 | X | There are currently 8 placeholders, all in Chapter 4
3 | Methodology | 20 | 25 | 32 | 53 | 22 | 0 | 0 | X | Make sure all captions are below, centered, etc. Same format as Figure 3.5
4 | Results and Analysis | 25 | 30 | 54 | 80 | 27 | 0 | 0 | X | Make sure all tables and figures fit in the margins
5 | Discussion and Conclusion | 3 | 5 | 81 | 85 | 5 | 0 | 0 | X | Make sure all captions fit on one line
R | References | 5 | 10 | 86 | 102 | 17 | 0 | 7 | X | Add the KG pictures
A | Appendices | 0 | 20 | 103 | 131 | 29 | 0 | 9 | X | Use Voyant-tools for EDA - basic information in the documents, in chapter 4
Total |  | 78 | 127 |  |  | 131 | 0 | 16 | X | Run experiments to fill placeholders
[9 empty] | X | Update text based on experiments
[9 empty] | X | Submit Chapter 4 to Dr. Elbasheer by October 15
[9 empty] | X | Get approval from Alex
[9 empty] | X | Get approval from Don
[9 empty] | X | Get approval from Andy
[9 empty] | X | Check consistency and completeness of each chapter
[9 empty] | X | Check consistency between chapters
[9 empty] | X | Check against department standards
[9 empty] | X | Complete appendices
[9 empty] | X | Check glossary and acronyms
[9 empty] | X | Print out and review with a highlighter
[9 empty] | X | Compare to similar Praxis
Submit final to Dr. Elbasheer by 11/1/2025
Submit final to Department by 11/4/2025
Prepare defense deck, Defense Sections - 25 slides - Half an hour
Introduction
Scope and objectives
Literature Review
Methodology
Results and data sets
Contribution and future direction
Conclusion
Dry run defense